## Sheet1
Risk | Mitigation in Sprint Cycle | Owner
**Hallucinated execution** | Sprint 3: Add "confidence scoring" DoD; Sprint 6: Policy engine validation gate | Pod 5 + Core
**Memory poisoning** | Red-team story in every 3rd sprint; automated lineage validation in ingestion pipeline | Pod 3 + Security
**Runaway costs** | Sprint 4: Token budget middleware; Sprint 8: Real-time cost dashboard with alerts | Pod 5
**Workflow instability** | Chaos engineering story quarterly; circuit breaker pattern in agent runtime | Pod 2
**Arabic NLP quality** | Dedicated "Arabic Quality" sprint every PI; native linguist in review loop | Strategic Pod
**Enterprise trust gap** | "Transparency Sprint" every 6 weeks: explainability demos, audit report generation | All Pods